## self-balancing robot
Self-Balancing Robot
Manage any type of project. Assign owners, set timelines and keep track of where your project stands.
Documents
Name | Subitems | Status | Owner | Due date | Notes | Timeline - Start | Timeline - End | Files
HARDWARE | V1.1 | [6 empty] | https://byui478393.monday.com/protected_static/29408086/resources/2138842828/Webble%20Wobbles%20Self%20Balancing%20Robot.pdf
Subitems | Name | Status | Files | Date
| V1.1 |  | https://byui478393.monday.com/protected_static/29408086/resources/2138845691/Webble%20Wobbles%20Self%20Balancing%20Robot.pdf | 2025-05-13
SOFTWARE | Software Block Diagram 1
Subitems | Name | Status | Files | Date
| Software Block Diagram 1 |  | https://byui478393.monday.com/protected_static/29408086/resources/2144242622/S-B_R_Software_Block_Diagram.drawio.pdf
SCHEDULE & GHANT PDFS
Next Sprint
Name | Subitems | Status | Owner | Due date | Notes | Timeline - Start | Timeline - End | Files
IMU and PID RND |  |  | Nicholas Petersen, Kyle Murdock |  |  | 2025-05-08 | 2025-05-22
IMU implementation, and calibration |  |  | Jamin Pottle, Nicholas Petersen
GPIO Assignments in Platformio |  |  | Hiram Benroth
[6 empty] | 2025-05-08 | 2025-05-22
Current Sprint
Name | Subitems | Status | Owner | Due date | Notes | Timeline - Start | Timeline - End | Files
Parts List | Motor w Encoders |  | Kyle Murdock, Nicholas Petersen | 2025-05-20 | ESP32, DC motors, wheels, chassis, ultrasonic sensor, camera, gyroscopic movement detector (inertia), IMU, PID controller | 2025-05-06 | 2025-05-20
Subitems | Name | Status | Files | Date
Motor w Encoders
Project Definition | Software Block Diagram,Hardware Block Diagram,Schedule,Hardware Responsibilites | Working on it |  | 2025-05-17 |  | 2025-05-07 | 2025-05-17
Subitems | Name | Status | Files | Date
| Software Block Diagram | Done
| Hardware Block Diagram | Done
Schedule
| Hardware Responsibilites | Done
Platformio Project on Git Hub |  | Working on it | Hiram Benroth
Chassis prototype MKI |  | Working on it | Wyatt Corrigan |  |  | 2025-05-08 | 2025-05-22
Part Aquisition// Finalization |  | Done | Jamin Pottle |  |  | 2025-05-08 | 2025-05-22
|  |  |  | 2025-05-17 to 2025-05-20 |  | 2025-05-06 | 2025-05-22
Completed
Name | Subitems | Status | Owner | Due date | Notes | Timeline - Start | Timeline - End | Files
1) Measure STC floor plan for simple grid coordinate system |  | Done
Feature List |  | Done | Jamin Pottle, Hiram Benroth | 2025-05-13 | Balance, go to destination, avoid obstacles. | 2025-05-06 | 2025-05-13
|  |  |  | 2025-05-13 |  | 2025-05-06 | 2025-05-13